# Project Approach

A CORE SPICE Asset

Table of Contents

Project Approach	0

1	Purpose	1

2	Scope	2

3	Assumptions and Constraints	2

4	Policy and Objectives	3

5	Roles, Responsibilities, and Assignments	4

6	Stakeholders	5

6.1	Internal Stakeholders	5

6.2	External Stakeholders	5

7	Meeting & Reporting Structure	5

7.1	Meetings	5

7.2	Reporting	6

8	Project Input	7

9	Outcomes	8

10	Lifecycle Management	12

11	Planning	13

12	Resources	13

13	Infrastructure Management	13

14	Risk Reduction	14

15	Related Approaches	14

16	Annexes	14

16.1	Acronyms and Glossary	14

16.2	References	15

# Purpose

The Project Approach establishes the foundation for managing the entire project lifecycle in alignment with CORE SPICE principles. It serves as the central coordinating document that integrates all other approaches and defines how the project will be executed to ensure quality, safety, security, and efficiency. This Approach is mandatory for all automotive system development projects and represents the implementation of all 12 CORE SPICE principles, particularly emphasizing:

- Safety first (Principle 1)

- Quality culture instead of formal control (Principle 3)

- Project over matrix (Principle 5)

- Risk minimization instead of risk management (Principle 7)

- Responsibility instead of control (Principle 10)

The Project Approach must be maintained throughout the project lifecycle and serves as the authoritative reference for project governance, coordination, and decision-making.

# Scope

The Project Approach must address the complete product development scope, including:

- System boundaries and interfaces are clearly defined

- Hardware, software, and mechanical components included in the project

- Safety classifications (ASIL levels) for all safety-relevant components

- Security classifications based on threat and risk assessment

- Key project phases from concept through production and maintenance

- Project deliverables and acceptance criteria

- Team structure and coordination mechanisms

- Delivery roadmap and release strategy

The Project Approach must include a clear definition of what is excluded from scope to prevent scope creep, and must address how scope changes will be managed during the project lifecycle.

# Assumptions and Constraints

<Outlines key assumptions and limitations for project execution, such as resource availability and compliance requirements.

Example:

Risk: Limited supplier availability.

Mitigation: Engage multiple suppliers.

Contingency: Stock critical components.

>

# Policy and Objectives

The project’s policies and objectives are grounded in CORE SPICE’s 5 pillars, 12 principles, and 5 common-sense practices. This ensures a practical, outcome-focused approach to project execution while meeting industry standards.

Policies:

Safety First (Pillar 1, Principle 1): Prioritize ISO 26262 compliance to ensure functional safety for autonomous and software-based components.

Quality Culture (Principle 3): Foster an immersive quality culture over formal control, integrating quality across all teams (Pillar 3: Organizational Empowerment).

Project Orientation (Pillar 2, Principle 5): Emphasize a projectized structure over matrix organizations, ensuring clear responsibilities (Principle 10: Responsibility Instead of Control).

Risk Minimization (Principle 7): Proactively reduce risks rather than merely manage them, maintaining long-term planning (Common Sense Practice 3: Time and Resource Plan).

Merit and Efficiency (Principle 11): Minimize bureaucracy, automate traceability (Principle 12), and focus on engineering skills (Principle 9).

Collaboration (Principle 6): Ensure deep customer involvement from day one to prevent escalations (Pillar 3).

Objectives:

Deliver <Product name> on time, within budget, and meeting all quality, safety, and security requirements.

Achieve ASIL <level> compliance for functional safety (ISO 26262) and cybersecurity compliance (ISO/SAE 21434).

Minimize project risks through proactive mitigation, targeting at least an 80% reduction in critical risks (Principle 7).

Ensure continuous partial deliveries to reduce late delivery risks (Principle 8: Ability to Deliver Instead of Final Delivery).

Foster a merit-based team culture, assembling teams based on skills (Principle 9) and ensuring 100% task responsibility assignment (Principle 10).

Implement automated traceability for at least 90% of requirements (Principle 12).

Conduct systematic needs and capability assessments for all project tasks (Common Sense Practices 1 and 2).

Maintain transparent progress tracking with automated status reports (Common Sense Practice 4).

Review all task completions for quality assurance, led by the TCC (Common Sense Practice 5).

<Extend here as applicable. Remove otherwise>

# Roles, Responsibilities, and Assignments

The following roles apply:

| Role | Responsibility | Assignment | Remarks |
| --- | --- | --- | --- |
| Project Lead | Defines, implements, and maintains the Project Approach; manages scope, team, and stakeholders | [Name] | This is the leading role in this Approach. |
| TCC | Ensures process compliance and CORE SPICE alignment | [Name] |  |
| Technical Lead | Provides technical oversight and coordinates discipline-specific activities | [Name] |  |
| VVT Lead | Oversees verification, validation, and testing activities | [Name] |  |

<Extend this list as needed. See also CORE SPICE Role Catalog for detailed role definitions>.

# Stakeholders

## Internal Stakeholders

<Lists internal stakeholders involved in project activities.

Example:

HR department

Work council

>

## External Stakeholders

<Lists external stakeholders involved in project activities.

Example:

OEM: Provides requirements.

Suppliers: Deliver components.

OEMs (e.g., for requirements and validation)

Suppliers (e.g., component providers)

Certification Bodies (e.g., for audits)

>

# Meeting & Reporting Structure

## Meetings

<Describes the meeting structure for project oversight and coordination.

Example:

Weekly Reviews: Monitor progress.

Steering Committee: Monthly updates.

>

## Reporting

<Defines project-specific reporting requirements.

Example:

Status Reports: Weekly updates on project progress, including milestones achieved, issues, and next steps, distributed to the Project Lead, TCC, and stakeholders (ISO/IEC/IEEE 16326:2019, Clause 6.2.7; ASPICE MAN.3, BP5: Report Progress; PMBOK Guide, Stakeholder Performance Domain).

Risk Reports: Monthly summaries of risk status, mitigation actions, and updates to the risk register, shared with the Project Sponsor, FuSa Manager, and OEM (ISO/IEC/IEEE 16326:2019, Clause 6.2.4; CORE SPICE Principle 7; PMBOK Guide, Measurement Performance Domain).

Quality Reports: Bi-weekly reports on quality metrics (e.g., defect rates, test coverage), distributed to the QA Manager and Technical Lead to ensure quality culture (ISO/IEC/IEEE 16326:2019, Clause 6.2.5; ASPICE MAN.3, BP5; CORE SPICE Principle 3).

Safety Reports: Monthly updates on safety milestone progress, ASIL compliance, and safety issues, shared with the FuSa Manager, Safety Analysts, and OEM (ISO 26262-2:2018, Clause 6.4.5; CORE SPICE Principle 1).

Cybersecurity Reports: Monthly summaries of threat modeling, security testing results, and compliance status, distributed to the Cybersecurity Analyst and OEM (ISO/SAE 21434:2021, Clause 8.4; CORE SPICE Principle 7).

Earned Value Management (EVM) Reports: Monthly analysis of cost and schedule performance (e.g., CPI, SPI), shared with the Project Sponsor and Project Lead to monitor budget adherence (ISO/IEC/IEEE 16326:2019, Clause 6.2.4; PMBOK Guide, Measurement Performance Domain).

Supplier Performance Reports: Quarterly evaluations of supplier quality, delivery, and compliance, distributed to the Supplier Lead and OEM (ASPICE ACQ.4, BP3: Monitor Supplier Performance; PMBOK Guide, Delivery Performance Domain).

Milestone Review Reports: Ad-hoc reports at key milestones, summarizing achievements, issues, and next steps, shared with all stakeholders (ISO/IEC/IEEE 16326:2019, Clause 6.2.2; PMBOK Guide, Measurement Performance Domain).

Automated Status Dashboards: Real-time dashboards (e.g., via Jira) showing project KPIs, accessible to all team members, ensuring transparency (ISO/IEC/IEEE 16326:2019, Clause 6.2.7; CORE SPICE Common Sense Practice 4; PMBOK Guide, Measurement Performance Domain).

>

# Project Input

<Lists inputs required for effective project management.

Example:

Customer Specifications: Detailed requirements for <Product name>, including functional, safety, and cybersecurity requirements, provided by the OEM in a requirements specification document (ISO/IEC/IEEE 16326:2019, Clause 6.3; ASPICE SYS.1, BP1: Identify Stakeholder Requirements; PMBOK Guide, Stakeholder Performance Domain).

Project Milestones: Key dates and deliverables defined by the customer, such as concept approval, prototype delivery, and production start, provided in a milestone schedule (ISO/IEC/IEEE 16326:2019, Clause 6.3; ASPICE MAN.3, BP2: Define Project Schedule; PMBOK Guide, Planning Performance Domain).

Safety Requirements: Safety goals, ASIL levels, and hazard analysis inputs for <Product name>, provided by the OEM or derived from HARA, in a safety requirements document (ISO 26262-3:2018, Clause 7.4.3; CORE SPICE Principle 1).

Cybersecurity Requirements: Security goals, threat scenarios, and cybersecurity requirements for <Product name>, provided by the OEM or derived from TARA, in a cybersecurity requirements document (ISO/SAE 21434:2021, Clause 9.5).

Quality Standards: Organizational quality standards and metrics (e.g., defect rates, test coverage), defined in the quality management system, ensuring a quality culture (ISO/IEC/IEEE 16326:2019, Clause 6.3; ASPICE MAN.3, BP1: Define Project Goals; CORE SPICE Principle 3).

Supplier Agreements: Contracts and Development Interface Agreements (DIAs) with suppliers, defining deliverables, timelines, and quality requirements, provided by the Supplier Lead (ISO/IEC/IEEE 16326:2019, Clause 6.3; ASPICE ACQ.4, BP1: Define Supplier Requirements; ISO 26262-2:2018, Clause 5.4.4).

Regulatory Requirements: Applicable regulations and standards (e.g., UNECE WP.29 for cybersecurity), provided by the OEM or regulatory bodies, in a compliance checklist (ISO/SAE 21434:2021, Clause 5.4.2).

Risk Register Template: Predefined template for risk identification and tracking, provided by the organizational risk management system, ensuring risk minimization (ISO/IEC/IEEE 16326:2019, Clause 6.3; CORE SPICE Principle 7; PMBOK Guide, Uncertainty Performance Domain).

Project Templates: CORE SPICE templates for plans (e.g., PMP, WBS), provided by the organizational process library, ensuring consistency (CORE SPICE Approaches; ISO/IEC/IEEE 16326:2019, Clause 6.2).

Stakeholder List: List of internal and external stakeholders (e.g., OEM, suppliers), provided by the Project Sponsor, ensuring collaboration (ISO/IEC/IEEE 16326:2019, Clause 6.3; CORE SPICE Principle 6; PMBOK Guide, Stakeholder Performance Domain).

Historical Data: Lessons learned and performance data from previous projects, provided by the organizational knowledge base, supporting continuous improvement (ISO/IEC/IEEE 16326:2019, Clause 6.3; CORE SPICE Principle 12; PMBOK Guide, Principle 12).

Resource Availability: Staffing, equipment, and budget constraints, provided by the Project Sponsor and HR, ensuring capability assessment (ISO/IEC/IEEE 16326:2019, Clause 6.3; Common Sense Practice 2; PMBOK Guide, Planning Performance Domain).

>

# Outcomes

The following goals apply to this Approach:

Organizational Management

- A Project Charter and Vision were established to define the project’s purpose, vision, and strategic alignment, ensuring stakeholder engagement.

- Value: A Project Charter establishes a clear purpose and strategic alignment from the start, providing developers with a shared roadmap that keeps everyone pulling in the same direction. It builds buy-in from stakeholders, making collaboration smoother. This aligns with CORE SPICE Principles 5 (Project Over Matrix) and 6 (Cooperation Instead of Confrontation).

- A Team Chart was created to define the hierarchical structure, roles, and reporting lines, fostering a projectized organization.

- Value: A Team Chart is a key element of effective project leadership. It clarifies roles, hierarchy, and reporting lines from day one, so developers know who to talk to for quick decisions. It empowers a project-focused setup where everyone owns their part. It eliminates blurriness and inertia, which are otherwise typical in matrix organizations. It is not about the “command and control”—it is all about effectiveness and development pace. This aligns with CORE SPICE Principles 5 (Project Over Matrix), 6 (Cooperation Instead of Confrontation), and 10 (Responsibility Instead of Control).

- The Role Catalog defines clear responsibilities and skills required to execute smoothly and at a high pace within the project. Refer to the standard CORE SPICE Team Chart for more details on the project structure.

- Value: A Team Chart is a key element of effective project leadership. It clarifies roles, hierarchy, and reporting lines from the outset, so developers know who to contact for quick decisions. It empowers a project-focused setup where everyone owns their part. It eliminates blurriness and inertia, which is otherwise typical in matrix organizations. It is not about the “command and control”—it is all about effectiveness and development pace. This aligns with CORE SPICE Principles 5 (Project Over Matrix), 6 (Cooperation Instead of Confrontation), and 10 (Responsibility Instead of Control).

Project Governance

- A feature-based Project Schedule and feature plan were established, including milestones, dependencies, and critical path analysis, and were continuously reviewed. That includes project lifecycle phases, such as production, operation, and decommissioning phases.

- Value: A feature-based Project Schedule maps out milestones and dependencies. It must be a core document that the team looks at in status meetings and planning discussions. It visualizes timelines and critical paths. It keeps the project focused. This aligns with CORE SPICE Principles 4 (Approaches Instead of Sequences of Tasks), 5 (Project Over Matrix), and 7 (Risk Minimization).

- A Work Breakdown Structure (WBS) was developed to decompose work into clear, owned components with defined dependencies, ensuring accountability.

- Value: A Work Breakdown Structure decomposes complex tasks into manageable pieces with clear ownership and dependencies. WBS elements (which can be viewed as “work packages”) define the responsibilities for work products. Every work product must be owned by a single person (not a “team”). This aligns with CORE SPICE Principles 4 (Process Approach), 5 (Project Over Matrix), 7 (Risk Minimization), and 10 (Responsibility Instead of Control).

- A Resource Plan was established to allocate staffing, equipment, and budget, ensuring capability assessment (ISO/IEC/IEEE 16326:2019, Clause 6.2.3; Common Sense Practice 2; PMBOK Guide, Planning Performance Domain).

- Value: A Resource Plan allocates staffing, equipment, and budget to match project needs. This prevents surprising resource shortages and aligns with CORE SPICE Principles 5 (Project Over Matrix), 9 (Engineering Skills Before Consensus), and 10 (Responsibility Instead of Control).

- A Stakeholder Communication Plan was defined to manage internal and external communication and to ensure collaboration (ISO/IEC/IEEE 16326:2019, Clause 6.2.7; CORE SPICE Principle 6; PMBOK Guide, Stakeholder Performance Domain).

Lifecycle Management

- Requirements and Design Specifications were developed (see System Engineering Approach and Software Engineering Approach).

Risk Management

- A Risk Management Strategy was defined and implemented, focusing on proactive risk identification and minimization.

- Value: A Risk Management Strategy identifies and minimizes risks early. That prevents project surprises, unnecessary task forces, and wasteful escalations. A well-defined and well-maintained risk approach increases team morale and helps retain key project members. This aligns with CORE SPICE Principles 3 (Quality Culture), 4 (Process Approach), and 7 (Risk Minimization).

- A Risk Register was maintained to document risks and mitigation strategies, ensuring transparency. It contains contingency plans for critical risk scenarios, ensuring preparedness.

- Value: A Risk Register tracks risks and mitigation strategies in one place. It helps recall project risks, ensuring that critical uncertainties, specific concerns, and potential undesirable events either never occur or occur in a controllable way. It provides transparency, allowing the team to focus on real threats. This aligns with CORE SPICE Principles 4 (Process Approach), 5 (Project Over Matrix), and 7 (Risk Minimization).

Compliance and Quality

- The QA Approach implemented compliance and Quality goals.

- Product quality was defined and implemented (see VVT Approach).

Functional Safety Compliance (for functional safety-relevant projects)

- Functional safety goals were defined and implemented in accordance with the FuSa Approach, ensuring compliance with ISO 26262.

Cybersecurity Compliance (for cybersecurity-relevant projects)

- Cybersecurity goals were defined and implemented as per the Cybersecurity Approach, ensuring compliance with ISO/SAE 21434.

Supplier and Partner Management

- Supplier goals were implemented as per the Supplier Management Approach.

Project Tracking and Reporting

- Automatically calculated project performance metrics and project status reports were established to measure progress and project health, ensuring transparency (ISO/IEC/IEEE 16326:2019, Clause 6.2.4; PMBOK Guide, Measurement Performance Domain).

Value: Automatically calculated metrics and status reports provide developers with real-time visibility into project health, enabling them to spot delays or bottlenecks early and avoid last-minute scrambles. They ensure transparency without manual hassle, freeing up time for the actual development and validation work. This aligns with CORE SPICE Principles 3 (Quality Culture), 4 (Process Approach), 7 (Risk Minimization), 11 (Merit Instead of Bureaucracy), and 12 (Automated Traceability).

Configuration and Change Management

- Configuration management goals were implemented as per the Configuration Management Approach.

Project Closure and Transition

- Project closure and handover criteria were defined to ensure completion readiness. A Project Closure Report was produced, summarizing the project and handing over to a series of support.

- Value: Defining project closure and handover criteria ensures all loose ends are tied up. That prevents post-project surprises or handover hassles that waste time. It keeps the team accountable for a clean finish. This aligns with CORE SPICE Principles 3 (Quality Culture), 4 (Process Approach), and 7 (Risk Minimization).

- A long-term Support plan was developed for ongoing maintenance.

- Value: A long-term Support plan ensures that ongoing maintenance is planned and resourced within a predefined period, including contractual and government obligations (if applicable). It prevents post-project surprises and costly fixes, especially after the key know-how carriers have left the organization. This aligns with CORE SPICE Principles 3 (Quality Culture) and 7 (Risk Minimization).

- A Lessons Learned Framework was established to capture and apply project insights.

- Value: Lessons learned capture project insights to avoid repeating mistakes, allowing developers to refine processes for smoother future work. This turns past frustrations into quick wins. This aligns with CORE SPICE Principles 3 (Quality Culture) and 7 (Risk Minimization).

<Extend this list if needed>

# Lifecycle Management

<Describes the lifecycle management process, integrating CORE SPICE methodology.

Example:

Concept: Define scope and risks.

Development: Execute sprints.

Closure: Document lessons learned.

>

# Planning

<Outlines integration of project activities into planning, including methodology, estimations, and feasibility.

Example:

Risk: Delayed milestones.

Mitigation: Align with the schedule.

Contingency: Adjust scope.

>

# Resources

<Lists resources required for project implementation.

Example:

Tools: Jira for tracking.

Personnel: Project Lead assigned.

CORE SPICE training

>

# Infrastructure Management

<Details infrastructure setup for project execution.

Example:

Tools: Secure repositories.

Access: Role-based permissions.

>

# Risk Reduction

<Defines strategies to identify and mitigate project risks, aligning with Principle 7.

Example:

Risk: Supplier delay.

Mitigation: Dual sourcing.

Contingency: Buffer stock.

>

# Related Approaches

The Project Approach serves as the central coordinating document for all other CORE SPICE Approaches.

FuSa Approach: Aligns safety goals.

Cybersecurity Approach: Integrates security.

Configuration Approach

VVT Approach

Issue Management Approach

Traceability Approach

Change Request Management Approach

Cyber Security Approach

QA Approach

Manufacturing Approach

Suppliers Approach

# Annexes

## Acronyms and Glossary

<Provides definitions for key terms used in the project.

Example:

WBS: Work Breakdown Structure.

ASIL: Automotive Safety Integrity Level.

>

## References

- CORE SPICE license: see “CORE SPICE Terms.pdf” in https://github.com/CORE-SPICE/CORE_SPICE_Releases

<Lists standards and documents referenced in the Approach.

Example:

ISO 16326: PMP requirements.

ISO 26262: Functional safety standard for road vehicles.

ISO/SAE 21434: Cybersecurity engineering for road vehicles.

ISO/IEC/IEEE 15288: System life cycle processes.

ISO/IEC/IEEE 12207: Software life cycle processes.

ISO 9001: Quality management systems – Requirements.

ISO 31000: Risk management – Guidelines.

ISO/IEC 29119: Software and systems engineering – Software testing.

ISO/IEC 27001: Information security management systems – Requirements.

IATF 16949: Quality management system requirements for automotive production.

VDA 6.3: Process audit standard for automotive suppliers.

IEC 61508: Functional safety of electrical/electronic/programmable electronic safety-related systems.

ISO 10007: Quality management – Guidelines for configuration management.

Customer Requirements Specification: Customer-specific requirements for <Product name>.

Customer Safety Requirements: Safety goals and ASIL levels for <Product name>.

Customer Cybersecurity Requirements: Cybersecurity requirements for <Product name>.

CORE SPICE Principles: 12 principles guiding project execution.

CORE SPICE Common Sense Practices: 5 practices for structured project tasks.

Automotive SPICE 4.0

>