# CRM Approach

A CORE SPICE Asset

Table of Contents

1	Purpose	2

2	Scope	2

3	Assumptions and Constraints	2

4	Policy and Objectives	3

5	Roles, Responsibilities, and Assignments	3

6	Stakeholders	4

6.1	Internal Stakeholders	4

6.2	External Stakeholders	5

7	Meeting & Reporting Structure	5

7.1	Meetings	5

7.2	Reporting	5

8	Project Input	6

9	Outcomes	6

10	Lifecycle Management	9

11	Planning	9

12	Resources	10

13	Infrastructure Management	10

14	Risk Reduction	10

15	Related Approaches	11

16	Annexes	11

16.1	Acronyms and Glossary	11

16.2	References	12

17	CORE SPICE Terms of Use	12

# Purpose

The Change Request Management Approach (CRM Approach) establishes a structured process to efficiently manage changes to the project's scope, requirements, and deliverables throughout the development lifecycle.

Its goals are to:

- Maintain system consistency and integrity across all artifacts.

- Minimize risks through thorough impact analysis.

- Ensure traceability between change requests (CRs) and affected work products.

- Support informed decision-making with clear data.

- Protect product quality, safety, and security via rigorous verification.

- Facilitate stakeholder communication and accountability.

- Optimize resource allocation and maintain compliance with standards.

- Align the CRs with the overall project schedule.

# Scope

This Approach governs the entire change request lifecycle—from identification to closure—across all project phases (e.g., design, development, testing). It applies to system, software, product quality, and hardware component changes, with a strong emphasis on traceability. Post-production maintenance changes are excluded unless specified in the project contract.

# Assumptions and Constraints

<assumptions and constraints like budget, resources, etc.

Example:

Assumptions:

- Stakeholders have access to a CR tracking system.

- CRs are submitted using standardized templates.

Constraints:

- Budget or organizational policies may limit tool options.

- Compliance with ISO 26262 (safety) and ISO 21434 (cybersecurity) are mandatory.

- It can be beneficial to define a "fast track" for very urgent or crucial CR's.

>

# Policy and Objectives

<

Example:

Policy:

- All scope changes require formal submission, review, and approval by the Change Control Board (CCB).

- Changes must preserve system integrity and traceability.

Objectives:

- Control project scope to prevent creep.

- Reduce risks through systematic evaluation.

- Ensure compliance with safety, security, and process standards.

- Improve efficiency with clear processes and automation.

>

# Roles, Responsibilities, and Assignments

The following roles apply:

| Role | Responsibility | Assignment | Remarks |
| --- | --- | --- | --- |
| Project Lead | Leads the CCB, approves CRs, oversees implementation | [Name] | This is the leading role in this Approach. |
| Configuration Lead | Establishes and maintains the Configuration Management Approach, manages baselines, and traceability | [Name] |  |
| TCC | Ensures process compliance and CORE SPICE alignment | [Name] |  |
| Project Lead | Oversees CM activities and approves major baselines | [Name] |  |
| Technical Lead | Provides technical input on artifact identification and changes | [Name] |  |
| VVT Lead | Ensures test artifacts are under configuration control and traceable | [Name] |  |

<Extend this list as needed. See also CORE SPICE Role Catalog for detailed role definitions>.

# Stakeholders

## Internal Stakeholders

<list of internal interfaces.
Example:

- All roles listed in Section 5

- Additional stakeholders: QA Teams, Management, and System Design Lead.

>

## External Stakeholders

<list of external interfaces.

Example:

- Customer representative

- Supplier(s)

- Regulatory Body (e.g., VDA)

>

# Meeting & Reporting Structure

## Meetings

<internal/external meetings, steering committee, etc.

Example:

- Weekly CCB Meetings: Review and decide on CRs (participants: CCB members).

- Ad-hoc Technical Reviews: Assess complex CRs (participants: Technical Lead, Developers, FuSa/Cybersecurity Analysts as needed).

>

## Reporting

<reporting structure.

Example:

- CR Status Reports: Weekly automated updates on CR status, aging, and resolution rates.

- Metrics Dashboard: Tracks cycle time, rework rates, and resource use (distributed to CCB and Management).

>

# Project Input

<definition of necessary inputs.

Example:

- CR submission forms.

- Impact analysis templates.

- Traceability matrices.

- Baseline documentation (requirements, design, test cases).

>

# Outcomes

The following outcomes for this approach apply:

- Change requests (CRs) were recorded, identified, and tracked from submission to closure, with status updates, decisions, and communications provided to stakeholders.

Value: Changes to the project scope must be carefully considered, as they often have financial implications. Carefully managing scope changes is one of the most underrated project activities, but it deserves top-level project leadership attention. Creating a change request should be a low-barrier activity—project teams should be encouraged to submit them, especially if they deliver additional value to key stakeholders (e.g., the customer). Well-organized CR management keeps stakeholders aligned and connected to the developing team during the project phase. It also minimizes risks. This aligns with CORE SPICE Principles 3 (Quality Culture) and 7 (Risk Minimization).

- Impacts of CRs on technical, safety, security, schedule, cost, and variant aspects were assessed, with dependencies identified, risks evaluated, and mitigation plans developed.

Value: Impact analysis may appear like an abstract concept, but it is simply an assessment of a project scope change that must be considered across all key project aspects, such as costs, current system stability, safety, and cybersecurity. By checking how change requests affect safety, security, and deadlines, you can prevent defects and surprises from derailing your work. It keeps the project on track with clear fixes. This aligns with CORE SPICE Principles 7 (Risk Minimization).

- CRs were reviewed, approved, and prioritized based on their impact, urgency, project and product risk assessment, and project requirements.

Value: Reviewing and prioritizing change requests based on impact and urgency helps make a rational decision on whether a change request makes financial, organizational, and architectural sense. A well-designed review process helps prevent costly mistakes and ensures safety, quality, and project stability. This aligns with CORE SPICE Principles 1 (Safety First), 3 (Quality Culture), and 7 (Risk Minimization).

Schedule

- The project schedule was adjusted to incorporate the approved change requests (CRs). The CR progress and its impacts were monitored, reported, and corrective actions taken as needed.

Value: Adjusting the schedule for change requests and monitoring progress helps keep the project on track and ensures adherence to the project schedule. Scheduling CRs should be part of the overall project scheduling activities. They could be handled similarly to features within the V-model. It ensures quality and minimizes delays. This aligns with CORE SPICE Principles 3 (Quality Culture) and 7 (Risk Minimization).

Traceability

- Bidirectional traceability was established and maintained between CRs and affected work products (e.g., requirements, designs, tests), with configuration baselines updated accordingly. See also the Traceability Approach.

Value: Traceability is the basis of a well-defined work product. It helps us maintain a clear, up-to-date view of the current baseline. CRs should be integrated into the overall Traceability Concept to prevent redundant project structures. This aligns with CORE SPICE Principles 3 (Quality Culture), 7 (Risk Minimization), and 12 (Automated Traceability).

Product Quality

- CR implementations were verified through testing, peer reviews, and regression testing, confirming correctness and preventing unintended effects (see VVT Approach).

Value: Once a CR is approved, it should be part of the regular workflow to prevent redundant project structures. It should be simply part of the VVT activities, scheduled in the same way as regular features. This aligns with CORE SPICE Principles 3 (Quality Culture) and 7 (Risk Minimization.

Configuration Management

- Changes were controlled through configuration management, as outlined in the CM Approach, with baselines established, modifications managed, and configuration completeness and consistency ensured (refer to the CM Approach for details).

Value: Since CRs belong to the regular Configuration Management Approach activities, this point is likely redundant. However, because of the emphasis on change request management by various standards, it is cited here as a "double-check." This aligns with CORE SPICE Principles 3 (Quality Culture) and 7 (Risk Minimization).

Requirements

- System and software requirements affected by Change Requests (CRs) were updated to ensure accuracy and completeness.

Value: Like the previous goal, change requests should be handled as part of the regular requirements flow. If the requirements are traced to CRs, the rest is just the regular V-procedure. Nevertheless, it is crucial to emphasize that no "ad-hoc" changes should be implemented, as this would take harmful shortcuts. This aligns with CORE SPICE Principles 3 (Quality Culture), 7 (Risk Minimization), and 10 (Responsibility Instead of Control)..

Metrics

- Metrics such as implementation time and resource utilization were collected and analyzed.

Value: Collecting metrics on time and resource spots issues like bottlenecks early. It speeds up work and improves quality. This aligns with CORE SPICE Principles 3 (Quality Culture) and 7 (Risk Minimization).

Functional Safety Compliance (for functional safety-relevant projects)

- Safety cases (per ISO 26262) and risk assessments (HARA) were reviewed, if applicable, for all active change requests (see FuSa Approach).

Cybersecurity Compliance (for cybersecurity-relevant projects)

- Threat Analysis and Risk Assessments (TARA, per ISO 21434) were reviewed and, if applicable, updated to reflect changes, ensuring compliance with cybersecurity standards (see Cybersecurity Approach).

<Extend this list if needed>

# Lifecycle Management

<Lifecycle to be applied and specific definitions/detailing. It may apply to the entire approach or a specific element of the project, such as bugs or tasks.

Example:

A CR lifecycle (as an Issue, see "Issue Management Approach for context):

| CR State | Possible Next States | Conditions |
| --- | --- | --- |
| Submitted | Under Review | CR is logged and assigned |
| Under Review | Approved, Rejected, Deferred | Based on CCB's decision |
| Approved | Implemented | An implementation plan is created |
| Rejected | Closed | CR is not pursued |
| Implemented | Verified | Change is implemented |
| Verified | Closed (if pass), Implemented (if fail) | Based on test results |
| Closed | (none) | CR is fully resolved and archived |

>

# Planning

<CR schedule (usually included in the overall schedule).

Example:

- CRs are prioritized based on impact and urgency.

- High-impact CRs are scheduled into sprints or change windows, with resources allocated accordingly.

>

# Resources

<list of used resources, e.g., tools, licenses, etc.

Example:

- Tools: CR tracking system (e.g., Jira, Azure DevOps).

- Personnel: CCB members, Developers, FuSa/Cybersecurity Analysts.

- Training: CR process and tool usage for all roles.

>

# Infrastructure Management

<tools, access rights, etc. required for CRM.

Examples:

- Tools integrate with requirements and test management systems for traceability.

- Access controls restrict CR submission and approval to authorized roles.

- Automated reporting provides real-time CR status updates.

>

# Risk Reduction

<how to determine and reduce risks in this approach.

Example:

- Risks: Scope creep, unverified changes, resource conflicts.

- Mitigations: Mandatory impact analysis, peer reviews, and traceability checks.

>

# Related Approaches

<related approaches and corresponding interfaces.

Example:

- Project Approach

- Systems Engineering Approach

- Software Engineering Approach

- Configuration Management Approach

- VVT Approach

- Issue Management Approach

- Traceability Approach

- Cybersecurity Approach

- QA Approach

>

# Annexes

## Acronyms and Glossary

<description of acronyms and terms.

Examples:

- CR: Change Request

- CCB: Change Control Board

- TARA: Threat Analysis and Risk Assessment

- VVT: Verification, Validation, and Testing

>

## References

- CORE SPICE license: see “CORE SPICE Terms.pdf” in https://github.com/CORE-SPICE/CORE_SPICE_Releases

<Standards and models to be applied, e.g., ASPICE, ISO 26262, other relevant standards, models, customer-relevant standards >